Title Slide
TaskJuggler Workshop
Chris Schlaeger
TaskJuggler Developer
cs@taskjuggler.org
Version: 1.0
Date: 2005-12-18
© 2005 Chris Schlaeger
Licensed under the GNU Free Document License 1.2

---
Workshop Agenda (Part I)
What is TaskJuggler?
Working with the User Interface
A first Project Plan
Generating a Report
Defining Resources
Defining Accounts
Capturing the Work Breakdown Structure
Using Shifts and Limits
Using Task Priorities to control the Scheduling
Working with Macros
Generating Reports

---
Workshop Agenda (Part II)
Working with Include Files
Creating Custom Templates
Advanced Reports
Collaborating with other Projects and Project Managers
Tracking the Project Status
Documenting the Project Evolvement
User defined Attributes
Playing with multiple Scenarios

---
TaskJuggler Workshop (Part I)

---
What is TaskJuggler?
Project was founded in 2001 by SUSE
OpenSource project with internal and external contributors
Website: http://www.taskjuggler.org
Until 2004 it was command line only
New graphical user interface was released in March 2005
Active user community from academia and industry
Discussion forums are available on the website
TaskJuggler is not a Gantt chart editor.
It's a project planning and tracking tool.

---
Working with the User Interface
Interactive Demonstration of the following features:
Launching TaskJuggler from the menu
Creating a new Project from a template file
Access to the manual and the F2 keyword help
Editor Settings
Auto-completion and indentation
Date insertion and modification with CTRL-D
Scheduling a project
Handling syntax and scheduling errors
Explanation of the list browsers and the editor and report tabs
Loading of an existing Project
Browsing of various reports
Demonstration of keyboard navigation to all GUI elements

---
Basic Components of a Project
Project Header
  - project myProject “My Project” “1.0”
  - 2005-11-01 2006-03-31
Task Definitions
  - task prjstart “Project Start” {
  - start 2005-11-05
  - }
  - task step1 “Step 1” {
  - depends prjstart
  - duration 2w
  - }

---
Specifying a Task Duration
Three methods of specifying a duration directly
  - Calendar time: duration
  - Working time: length
  - Resource time: effort
Must be used with a unit
  - min, h, d, w, m, y
Examples:
  - duration 1.5y (1.5 calendar years)
  - length 2w (10 working days)
  - effort 2w (10 resource days)
Conversion factors: yearlyworkingdays, dailyworkinghours

---
The Easiest Linux to Deploy and Maintain
Exercise No. 1
Task:
Create a project plan consisting of 5 different tasks.
Time: 10 minutes
Steps
Create a project with the “Blank” Template
Enter 5 tasks with different task durations
4 should happen in sequence
1 should happen simultaneously with another task
Schedule the project and make sure there are no errors
The summary report should show a task count of 5

---
Generating a Report
Available Format Types
  - Interactive, HTML, CSV, XML, Export, iCalendar
Available Content Types
  - Task Reports, Resource Reports, Account Reports, Calendar Reports, Status Reports
Definition of a Report
  - resourcereport “Resource List”
  - taskreport “Project Overview” {
  - columns no, name, start, end, chart
  - }

---
Using Flags to mark Objects
Use flags to mark certain groups of tasks.
Flags must be declared before they can be used.
Flag names are TaskJuggler IDs. They must consist only of letters, numbers and underscores.
  - flags important
  - task foo “Foo Task” {
  - flags important
  - }

---
Filtering of Report Content
Content of reports can be limited to the exact amount needed.
Show only columns you are interested in
Show only tasks you are interested in
  - hidetask important
Show only resources you are interested in
  - hideresource ~team
Sort content by up to 3 criteria
  - sorttasks tree, startup
  - sortresources nameup

---
Getting Help
The TaskJuggler Manual
  - Available as PDF document
  - On the web: http://www.taskjuggler.org/docs.php
  - In the menu: Select Help->TaskJuggler Handbook or Press F1
  - Context sensitive keyword help:
    - Move the cursor in the editor over any TaskJuggler keyword and press F2. You will get a detailed explanation of the keyword including it's meaning, context and other related information.

---
Structure of a TaskJuggler Project
TaskJuggler processes files from top to bottom. So the order of things inside the file matter. You cannot reference properties, that haven't been defined yet. The following order is a good guideline:
  - Project Header
  - Macro definitions
  - Flag declarations
  - Shift definitions
  - Account definitions
  - Resource definitions
  - Task definitions
  - Bookings
  - Reports

---
Exercise No. 2
Task:
Generate a report for your first project.
Time: 5 minutes
Steps
Look up the possible columns in the TaskJuggler manual
Be sure to include the start and end date of tasks in the report
Use flags to filter out 2 tasks
Sort the remaining tasks by name from last to first

---
Defining Resources
Resource definitions have similar format as task definitions
Many attributes get inherited from enclosing scope.
  - resource team “Developer Team” {
  - rate 300	# daily cost
  - resource john “John Doe”
  - resource wilma “Wilma Flintstone”
  - resource paul “Paul McCartney” {
  - rate 250
  - }
  - }

---
Assigning Resources to Tasks
Simple case: 1 task, 1 resource
  - task foo “Foo Task” {
  - effort 5d
  - allocate joe
  - }
Allocating multiple resources
  - task foo “Foo Task” {
  - effort 10w
  - allocate wilma, paul, joe
  - }

---
Assigning Resources to Tasks (Cntd.)
Allocating a team
  - task foo “Foo Task” {
  - effort 5d
  - allocate team
  - }
Mandatory allocations
  - task foo “Foo Task” {
  - effort 10w
  - allocate wilma
  - allocate projector { mandatory }
  - }

---
Assigning Resources to Tasks (Cntd.)
Specifying alternative resources
  - task foo “Foo Task” {
  - effort 5d
  - allocate joe { alternative paul }
  - }
Using the selection function
  - task foo “Foo Task” {
  - effort 5d
  - allocate wilma {
  - alternative joe, paul
  - select maxloaded
  - }
  - }

---
Assigning Resources to Tasks (Cntd.)
Making sure that a resource does not change once it has been selected
  - task foo “Foo Task” {
  - effort 5d
  - allocate wilma {
  - alternative joe, paul
  - persistent
  - }
  - }
Whichever resource is available first, does all of the work.

---
Resource Efficiency
You can specify differences in the ability to do work by using the efficiency attribute. Use with care as this can lead to micromanagement!
You can model an opaque team of 5 people
  - resource team “5 Guys” {
  - efficiency 5.0
  - }
You can model resources that don't do any work
  - resource projector “Projector” {
  - efficiency 0.0
  - }

---
Timing Resolution
By default TaskJuggler uses 1 hour time slots.
This can be changed using the timingresolution keyword.
All time values are always rounded to a timing resolution boundary.
Changing this value has a massive influence on performance and memory consumption.
  - project myproject “My Project” “1.0”
  - 2005-11-04 2006-03-06 {
  - timingresolution 10min
  - }

---
Commenting your Project
Comments allow you to put any additional information about your project right into the project file.
There are 2 types of comments:
  - Single line comment: # Some wise words
  - Multi-line comments:
    - /* A whole lot of
    - * more wise
    - * words */
Comments can be used to temporarily disable certain parts of the project file.

---
Exercise No. 3
Task:
Plan 2 meetings for 2 different teams each so TaskJuggler prevents conference room conflicts.
Time: 10 minutes
Steps
Define 2 teams with at least 3 members each
Define 2 conference rooms
Define the meeting tasks each lasting 2.5 hours
Allocate the teams and meeting rooms appropriately.

---
Short Break
Please be ready to continue in 5 Minutes!

---
Name Spaces
TaskJuggler properties like Tasks, Accounts and Resources have separate name spaces.
It's ok to have a task and a resource with ID foo.
The Task name space is hierarchical. All other name spaces are flat.
There can be a task foo.foo, but not a resource.
  - task foo “Foo” {
  - task foo “Foo” // This is ok!
  - }
  - resource foo “Foo” {
  - resource foo “Foo” // This is an error!
  - }

---
Defining Accounts
Format for Account definitions
  - account acc1 “Cost Accounts” cost {
  - account salaries “Salary cost”
  - account material “Material cost”
  - }
  - account acc2 “Revenue Accounts” revenue {
  - account payments “Customer Payments”
  - }

---
Crediting Costs to Accounts
Cost Type 1: Running costs
  - task job “A Job” {
  - effort 2w
  - allocate joe
  - account salaries
  - }
Cost Type 2: Start or End payments
  - task payment “Customer Payment” {
  - start 2005-12-24
  - milestone
  - startcredit 50000
  - account payments
  - }

---
Accounting Reports
Currency unit must be defined in the project header
  - project myProjectId "My Project" "1.0"
  - 2005-11-02 2005-12-31 {
  - currency "$"
  - currencyformat "(" ")" "," "." 2
  - }
Accounting Reports are currently available in HTML or CSV
  - htmlaccountreport “Project-Cash-Flow.html” {
  - columns no, name, total, monthly
  - accumulate
  - }

---
Exercise No. 4
Task:
Calculate the P&L for a 3 year project taking development costs and expected customer payments into account.
Time: 15 minutes
Steps
Define the project outline with 4 consecutive tasks.
Define an opaque team of 5 people and assign them to all tasks
Define 3 customer payments as milestones.
Define cost and revenue accounts.
Create an accounting report that shows your cash flow.

---
Milestones
Tasks that don't have any kind of duration specification are called milestone.
You can mark a task to be a milestone, but it still must not have any duration specification.
  - task foo “Foo Task” {
  - start 2005-11-04
  - }
  - task foo “Foo Task” {
  - start 2005-11-04
  - milestone
  - }

---
Capturing the Work Breakdown Structure
Start with a project outline
  - task project “My Project” {
  - start 2005-11-01
  - task plan “Planning Phase” {
  - task prd “Write PRD” {
  - duration 2w
  - }
  - }
  - task dev “Development Phase”
  - task qa “Testing Phase”
  - task rel “Release Phase”
  - task maint “Maintenance Phase”
  - }
Then add details as you learn them.

---
Specifying Task Dependencies
Task B depends on Task A
  - task a “Task A” { start 2005-11-01 }
  - task b “Task B” { depends a }
Task A precedes Task B
  - task a “Task A” { precedes b }
  - task b “Task B” { start 2005-11-01 }
Relative and absolute Dependency Specifications
  - task p “Project” {
  - task a “Task A” { start 2005-11-01 }
  - task b “Task B” { depends !a }
  - task c “Task C” { depends p.b }
  - }

---
Scheduling Direction
Attributes that cause ASAP scheduling:
  - start, depends
Attributes that cause ALAP scheduling:
  - end, precedes
Explicit specification of the scheduling mode:
  - scheduling asap
  - scheduling alap
The last implicit or explicit specification rules
Avoid mixing ASAP and ALAP tasks in the same project! Either plan from start to end or vice versa.

---
Logical Expressions for Filters
Logical Filter expressions consist of flags, functions and operators
Supported operators (subset):
  - & (and), | (or), ~ (not), > (larger), < (smaller)
Expressions can be grouped with parentheses
Many query functions supported
  - e.g. isChildOf(ID), isMilestone(), treeLevel()
Example:
  - taskreport “Task Overview (Important ones)” {
  - rolluptask (treelevel() > 1) & ~important
  - }

---
Exercise No. 5
Task:
Create a release plan for a software project that outlines the project phases. Generate a report with only the important milestones.
Time: 15 minutes
Steps
All tasks should be relative to a start milestone
Start with an outline of the phases
Add more detailed tasks
Mark important milestones
Generate the report
Then change the start date and watch the impact on the report.

---
Short Break
Please be ready to continue in 5 Minutes!

---
Defining Working Hours
Global definition in the Project Header
  - project myprj “My Project” “1.0” 2005-11-01 2006-04-01 {
  - workinghours {
  - mon 8:00 – 12:00, 13:00 – 17:00
  - tue 8:00 – 12:00, 13:00 – 17:00
  - wed 8:00 – 12:00, 13:00 – 17:00
  - thu 8:00 – 12:00, 13:00 – 17:00
  - fri 8:00 – 12:00, 13:00 – 17:00
  - sat off
  - sun off
  - }
  - }

---
Defining Working Hours (Cntd.)
Different working hours for some resources
  - resource team “Team” {
  - workinghours {
  - mon off
  - fri 8:00 – 12:00
  - }
  - resource john “John Doe” {
  - workinghours {
  - mon 13:00 – 17:00
  - }
  - }
  - resource wilma “Wilma Flintstone”
  - }

---
Defining Shifts
Shifts are defined sets of working hours per week
  - shift fullTime “Full Time Shift” {
  - workinghours mon 8:00 – 12:00, 13:00 – 17:00
  - workinghours tue 8:00 – 12:00, 13:00 – 17:00
  - workinghours wed 8:00 – 12:00, 13:00 – 17:00
  - workinghours thu 8:00 – 12:00, 13:00 – 17:00
  - workinghours fri 8:00 – 12:00, 13:00 – 17:00
  - workinghours sat off
  - workinghours sun off
  - shift partTime “Part Time Shift” {
  - workinghours mon off
  - workinghours wed off
  - }
  - }

---
Using Shifts
Shifts are used to modify standard working hours during specified intervals
  - resource wilma “Wilma Flintstone” {
  - shift partTime 2005-12-01 – 2006-01-01
  - }
Shifts can be used to limit resource allocations to a task during certain intervals
  - task foo “Foo Task” {
  - effort 2w
  - allocate john
  - shift partTime 2005-12-01 – 2006-01-01
  - }

---
Limiting Resource Usage per Interval
Limits can be used to limit the usage of a resource or an allocation of resources to a task to a certain maximum per interval. Supported intervals are day, week or month.
  - resource john "John Doe" {
  - limits { dailymax 2h weeklymax 6h }
  - }
  - task foo "Foo Task" {
  - duration 60d
  - allocate r2 {
  - limits { weeklymax 3d monthlymax 2w }
  - }
  - }

---
Using Task Priorities to control the Scheduling
The priority attribute controls the probability that a tasks gets the allocated resources
The default priority is 500
  - task secUpds “Security Updates” {
  - duration 2m
  - allocate paul
  - limits { dailymax 1h }
  - priority 700
  - }
  - task calls “Handle customer calls” {
  - duration 2m
  - allocate paul
  - priority 300
  - }

---
Exercise No. 6
Task:
Create a shift plan for the next 4 weeks for a team of system administrators.
Time: 15 minutes
Steps
Define the various tasks of the system administration group
Define your team
Prioritize the tasks and allocate the resources
Generate a shift plan for one of the team members that only list his or her tasks
Generate an overview plan that shows all assignments

---
End of TaskJuggler Workshop (Part I)

---
TaskJuggler Workshop (Part II)

---
Workshop Agenda (Part II)
Working with Include Files
Creating Custom Templates
Advanced Reports
Collaborating with other Projects and Project Managers
Tracking the Project Status
Documenting the Project Evolvement
User defined Attributes
Playing with multiple Scenarios

---
Working with Macros
Macros are somewhat flexible text fragments that can be inserted multiple times once they have been defined.
Macro names must have at least one uppercase letter
Definition of a Macro
  - macro allocateGrp [ allocate john, wilma ]
Using a defined Macro
  - task foo “Foo Task” {
  - effort 20d
  - ${allocateGrp}
  - }

---
Working with Macros (Cntd.)
Parts of macros can be replaced during insertion time by using parameters.
Definition of a Macro with parameters
  - macro defTask [ task ${1} “${1} Task” ]
Calling a Macro with parameters
  - ${defTask “foo”}
  - ${defTask “bar”}
Result of the expanded Macros
  - task foo “foo Task”
  - task bar “bar Task”

---
Creating Custom Templates
TaskJuggler comes with several custom templates but the you can add your own templates as well
Custom templates need to be put into
  - ${HOME}/.kde/share/apps/taskjuggler/templates/en_US
The project start and end date can be automatically set to the current date (and current date + 180 days) when using @@projectstart@@ and @@projectend@@ instead of the dates in the templates.

---
Working with include Files
To include another file into your project file, put an include statement into your project:
  - include “sometasks.tji”
Project files must have a .tjp extension, include files must have a .tji extension.
Tasks in the include file can be included as sub-tasks of some other task.
  - include “sometasks.tji” { taskprefix foo }
Include statements may only be used in the project header or outside of all property definitions.
supplement keyword can be used to add attributes to already defined properties

---
Exercise No. 7
Task:
Take the release plan project and break it into several files.
Time: 15 minutes
Steps
Create an include file for the resource definitions divided into 2 teams
Add some sub tasks of one tasks into 2 additional include files
Allocate some resources so that one team is allocated in each of the include files
Learn how to navigate the project with the browsers

---
Advanced Reports
Good reports show exactly the amount of information you want to show. Nothing more and nothing less.
TaskJuggler supports many filter mechanism to limit the reports to the right amount of data
  - Show only the columns that matter
  - hidetask, hideresource, hideaccount
  - rolluptask, rollupresource, rollupaccount
  - limit the report interval with start and end dates
  - values are reported in the right format and unit:
    - loadunit, timeformat, shorttimeformat, barlabels, showprojectids
In tree-mode sorting parents are always included, no matter what the filters say. Use a different sorting mode to avoid this if undesired.

---
Advanced Reports (Cntd.)
The default scenario ID needed for some query functions is plan
In tree-mode sorting parents are always included, no matter what the filters say. Use a different sorting mode to avoid this if undesired.

---
Customizing Column Headers and Cells
The default column title can be replaced
  - taskreport “Task List” {
  - columns no, name, effort { title “Work” }
  - }
In HTML reports links can be added to headers and table cells
  - htmltaskreport "LinkURL.html" {
  - columns hierarchindex, name,
  - monthly { subtitleurl "Monthly-Detail-$${month}.html" }
  - }
  - htmltaskreport "LeafEfforts.html" {
  - columns hierarchindex, name,
  - effort { hidecelltext ~isLeaf() }
  - }

---
Adding Information to Reports
Adding a Headline
  - taskreport “Task List” {
  - headline “The tasks of my project”
  - }
Adding a Caption
  - htmlresourcereport “Resources.html” {
  - caption “List of all the hard working men and women on the project.”
  - }
Adding a copyright (must be done in the header)
  - project myPrj “My Project” “1.0” 2005-11-01
  - 2006-04-01 {
  - copyright “2005 Big Business, Inc.”
  - }

---
Advanced HTML Reports
HTML Reports can be customized by adding an inline stylesheet, and HTML fragments at the top and bottom of the report.
rawhead
'<table align="center" border="2" cellpadding="10"
style="background-color:#f3ebae; font-size:105%">
<tr>
<td><a href="Tasks-Overview.html">Tasks Overview</a></td>
<td><a href="Staff-Overview.html">Staff Overview</a></td>
<td><a href="Accounting.html">Accounting</a></td>
<td><a href="Calendar.html">Calendar</a></td>
</tr>
</table>
<br>'

---
CSV (Colon Separated Values) Report
CSV is a simple text-form exchange format to export data to office suites like OpenOffice.org
CSV reports are available in 3 types
  - csvtaskreport
  - csvresourcereport
  - csvaccountreport
Right click on a CSV report in the report browser and select “Generate Report”
Then the resulting report file can be loaded with OpenOffice.org. Use “comma” as a separator.
Set the mime-type definition of text/x-csv to OpenOffice.org to automatically lauch OOo from the report browser

---
Exercise No. 8
Task:
Generate several different reports for your project.
Time: 10 minutes
Steps
Generate an HTML task report that only contains tasks allocated to team 1
Generate a CSV report with all tasks and efforts and import it into OpenOffice.org

---
Short Break
Please be ready to continue in 5 Minutes!

---
Tracking the Project Status
TaskJuggler is helping you a lot when tracking your project status. If no other information is provided, it assumes that all tasks have progressed as planned.
Simple way to provide status information
  - task foo “Foo Task” {
  - effort 2w allocate john
  - complete 75
  - }
Detailed way to provide status information
  - supplement resource john {
  - booking 2003-06-08 2003-06-09 t1 { sloppy 2 }
  - booking 2003-06-11 2003-06-12 t1 { sloppy 2 }
  - }

---
Generating Export Files
TaskJuggler can export a scheduled project in the same text format that the unscheduled project was provided in.
The amount of information that is exported can be controlled by the properties attribute.
E.g. export only the resource bookings for a certain week:
  - export "Week1Bookings.tji" {
  - properties bookings
  - start 2000-01-01
  - end 2000-01-08
  - }

---
Scheduling in Projection Mode
The bookings up to the current date may vary from the original plan.
TaskJuggler can then schedule a new plan based on the amount of work that has happened already.
The “current” date is user configurable.
  - project prj "Project" "1.0" 2003-06-05
  - 2003-07-05 {
  - now 2003-06-15
  - scenario plan "Plan" {
  - projection
  - }
  - }

---
Generating Status Reports
Status reports are only available in HTML format
Status reports include the following items
  - Tasks that should have been finished already
  - Work in progress
  - Tasks that have been completed
  - Upcoming new tasks
  - htmlstatusreport “StatusReport-Week45.html”

---
Exercise No. 9
Task:
Generate a status report report for the project 4 weeks after the start.
Time: 15 minutes
Steps
Export bookings for the first 4 allocated weeks
Remove or modify some bookings and include the export file in your project file
Generate a status report for the week 4 weeks after the first work started
Generate a new project plan based on the currently completed work

---
Working with multiple Project Plans
Export reports can be standalone project files or includeable sub-projects depending on the filename extension used in the report definition.
  - export "SubProject.tji" {
  - taskattributes all
  - hideresource 0
  - }
  - export "FullProject.tjp" {
  - taskattributes all
  - hideresource 1
  - }

---
Different Export Files
*.tjp Export files have a project header
*.tji Export files have no project header
The other content can be controlled by properties and the usual filter mechanisms
The following properties are supported:
  - all, bookings, shifts, tasks, resources

---
Dealing with multiple Project IDs
All tasks of sub-projects keep their original project ID
To include a sub-project, the project ID needs to be declared first
  - projectids myproject1, myproject2
Export reports (*.tji) already contain this declaration

---
Exporting a sub-Project
Parts of a project can be turned into a standalone Project file.
Use taskroot to identify the sub-tree you want to export. All sub tasks of the root task will be exported.
  - export “SubProject.tjp” {
  - taskroot myproject.jimsWork
  - taskattributes all
  - hideresource 0
  - }
Use hidetask to export only certain sub-tasks of the root task
  - hidetask ~isChildOf(myproject.jimsWork.foo)

---
Exercise No. 10
Task:
Combine 2 independent project into a summary project.
Time: 15 minutes
Steps
Turn the 2 task files into independent projects
Export the scheduled projects
Include them into a summary project
Generate a summary report

---
Short Break
Please be ready to continue in 5 Minutes!

---
Documenting the Project Evolvement
Adding notes to tasks
  - task foo “Foo Task” {
  - note “This might be difficult.”
  - }
Adding status notes to tasks
  - task foo “Foo Task” {
  - statusnote “We have unexpected problems.”
  - }
Keeping a Journal of events
  - task foo “Foo Task” {
  - journalentry 2005-10-20 “We ran into problems.”
  - journalentry 2005-10-21 “Informed customer.”
  - journalentry 2005-10-25 “Problem solved.”
  - }

---
User Defined Attributes
The attribute set of tasks, resources and accounts can be extended by the user.
There are two types of attributes available
  - Strings and URLs
User defined attributes do not impact the scheduling. They are for documentation and reporting purposes only.
They can be used in all reports like the build-in attributes.
User Defined attribute IDs must start with a capital letter

---
User Define Attributes (Cntd.)
project ca "Custom Attributes" "1.0" 2003-05-28
2003-06-28 {
extend task {
reference MyLink "My Link"
text MyText "My Text"
}
}
task t "Task" {
start 2003-05-28
MyLink "http://www.taskjuggler.org" { label "TJ Web" }
MyText "TaskJuggler is great!"
}

---
Playing with multiple Scenarios
project prj "Example" "1.0" 2005-05-29 2005-07-01 {
scenario plan "Planned Scenario" {
scenario actual "Actual Scenario"
scenario test "Test Scenario" {
disabled
}
}
}
task t "Task" {
start 2005-05-29
actual:start 2005-06-03
test:start 2005-06-07
}

---
Exercise No. 11
Task:
Add another slightly different scenario to the project plan from Exercise 7.
Time: 15 minutes
Steps
Create an additional scenario definition
Look in the manual for scenario specific values
Add a few changes for the 2nd scenario
Add an email attribute to your resources
Generate an HTML task report that compares both scenarios
Generate a list with all resources including their email address

---
Logo
The End
Thanks for attending!
A copy of the slides is available from the TaskJuggler web site at http://www.taskjuggler.org/

---
Disclaimer Slide
© 2005 Chris Schlaeger
Permission is granted to copy, distribute and/or modify this document under the terms of the GNU Free Documentation License, Version 1.2 published by the Free Software Foundation; with no Invariant Sections, no Front-Cover Texts and no Back-Cover Texts. A copy of the license is available at http://www.fsf.org/licensing/licenses/fdl.txt.